## Steps
Presentation (25 pts)
Section | Actions | Tony | Jenny | Jacqueline | Due | Complete
Content | Selected topic | x | x | x | 2022-02-02 | 2022-01-26
| Reason the topic was selected | x | x | x | 2022-02-02 | 2022-01-26
Description of the source of data
| Questions the team hopes to answer with the data | x | x | x | 2022-02-02 | 2022-01-26
Description of the data exploration phase of the project
Description of the analysis phase of the project
Technologies, languages, tools, and algorithms used throughout the project
Result of analysis
Recommendation for future analysis
Anything the team would have done differently
Slides | Slides are primarily images or graphics (rather than primarily text)
Primarily images or graphics (rather than primarily text)
Images are clear, in high-definition, and directly illustrative of subject matter
Live Presentation | All team members present in equal proportions.
The team demonstrates the dashboard's real-time interactivity.
The presentation falls within any time limits provided by the instructor.
The submission includes speaker notes, flashcards, or a video of the presentation rehearsal.
GitHub Repository (10 pts)
Section | Actions |  |  |  |  | Complete
Main Branch | All code in the main branch should be production-ready
All code should be clean, commented, easy to read, and adhere to a coding standard, such as PEP8
All code necessary to perform exploratory analysis
All code necessary to complete the machine learning portion of the project
Any images that have been created (at least three)
Requirements.txt file
README.md | Cohesive, structured outline of the project (this may include images, but they should be easy to follow and digest)
Link to dashboard (or link to video of dashboard demonstration)
Link to Google Slides presentation
The descriptions and explanations required in all other project deliverables should also be in your README.md
Individual Branches | At least one branch for each team member
Each team member has at least four commits for the duration of the final segment (16 total commits per person)
Machine Learning Model (25 points)
Section | Actions |  |  |  |  | Complete
N/A | Description of data preprocessing
Description of feature engineering and the feature selection, including the team's decision-making process
Description of how data was split into training and testing sets
Explanation of model choice, including limitations and benefits
Explanation of changes in model choice (if changes occurred between the Segment 2 and Segment 3 deliverables)
Description of how the model was trained (or retrained if the team used an existing model)
Description and explanation of model's confusion matrix, including final accuracy score
Addresses the question or problem the team is solving
If statistical analysis is not included, add a description of how it would be included in the next phases of the project.
Seg #1: create a model mockup, importing data in the desired format and exporting data in the required format
Seg #2-3: train your model and confirm it's working with your robust database
Seg #4: submit your machine learning model, the description and working code, as well as the following information
Database Integration (25 pts)
Section | Actions |  |  |  |  | Complete
N/A | Seg #1: create a mockup or "dummy" database during the first segment of your project to make sure the model works
This mockup will follow the format of the expected database, but it will be simpler and likely in a CSV or JSON format
The following is for the final segment:
Stores static data for use during the project
Interfaces with the project in some format (e.g., scraping updates the database, or database connects to the model)
Includes at least two tables (or collections if using MongoDB)
Includes at least one join using the database language (not including any joins in Pandas)
Includes at least one connection string (using SQLAlchemy or PyMongo)
If you use a SQL database, you must provide your Entity Relationship Diagram (ERD) with relationships
Dashboard (15 pts)
Section | Actions |  |  |  |  | Complete
N/A | Images from the initial analysis
Data (images or report) from the machine learning task
At least one interactive element
Either the dashboard is published or the submission includes a screen capture video of it in action

## Presentation (25 pts)
Presentation (25 pts)
Section | Actions | Complete
Content | Selected topic
Reason the topic was selected
Description of the source of data
Questions the team hopes to answer with the data
Description of the data exploration phase of the project
Description of the analysis phase of the project
Technologies, languages, tools, and algorithms used throughout the project
Result of analysis
Recommendation for future analysis
Anything the team would have done differently
Slides | Slides are primarily images or graphics (rather than primarily text)
Primarily images or graphics (rather than primarily text)
Images are clear, in high-definition, and directly illustrative of subject matter
Live Presentation | All team members present in equal proportions.
The team demonstrates the dashboard's real-time interactivity.
The presentation falls within any time limits provided by the instructor.
The submission includes speaker notes, flashcards, or a video of the presentation rehearsal.

## GitHub Repository (10 pts)
GitHub Repository (10 pts)
Section | Actions | Complete
Main Branch | All code in the main branch should be production-ready
All code should be clean, commented, easy to read, and adhere to a coding standard, such as PEP8
All code necessary to perform exploratory analysis
All code necessary to complete the machine learning portion of the project
Any images that have been created (at least three)
Requirements.txt file
README.md | Cohesive, structured outline of the project (this may include images, but they should be easy to follow and digest)
Link to dashboard (or link to video of dashboard demonstration)
Link to Google Slides presentation
The descriptions and explanations required in all other project deliverables should also be in your README.md
Individual Branches | At least one branch for each team member
Each team member has at least four commits for the duration of the final segment (16 total commits per person)

## Machine Learning Model (25 pts)
Machine Learning Model (25 points)
Section | Actions | Complete
N/A | Description of data preprocessing
Description of feature engineering and the feature selection, including the team's decision-making process
Description of how data was split into training and testing sets
Explanation of model choice, including limitations and benefits
Explanation of changes in model choice (if changes occurred between the Segment 2 and Segment 3 deliverables)
Description of how the model was trained (or retrained if the team used an existing model)
Description and explanation of model's confusion matrix, including final accuracy score
Addresses the question or problem the team is solving
If statistical analysis is not included, add a description of how it would be included in the next phases of the project.
Seg #1: create a model mockup, importing data in the desired format and exporting data in the required format
Seg #2-3: train your model and confirm it's working with your robust database
Seg #4: submit your machine learning model, the description and working code, as well as the following information

## Database Integration (25 pts)
Database Integration (25 pts)
Section | Actions | Complete
N/A | Seg #1: create a mockup or "dummy" database during the first segment of your project to make sure the model works
This mockup will follow the format of the expected database, but it will be simpler and likely in a CSV or JSON format
The following is for the final segment:
Stores static data for use during the project
Interfaces with the project in some format (e.g., scraping updates the database, or database connects to the model)
Includes at least two tables (or collections if using MongoDB)
Includes at least one join using the database language (not including any joins in Pandas)
Includes at least one connection string (using SQLAlchemy or PyMongo)
If you use a SQL database, you must provide your Entity Relationship Diagram (ERD) with relationships

## Dashboard (15 pts)
Dashboard (15 pts)
Section | Actions | Complete
N/A | Images from the initial analysis
Data (images or report) from the machine learning task
At least one interactive element
Either the dashboard is published or the submission includes a screen capture video of it in action

## Sheet1
Segment | Description | ▪ | ● | p | ▪ | ● | p
1 | Decide on your overall project, select your question, and build a simple model. Connect model to fabricated database using (CSV) or (JSON) to prototype your idea. |  |  |  | Set up repository |  | Create machine learning model
2 | Train your model and build out the database you'll use for your final presentation. |  |  |  | Name repository
3 | Connect your final database to your model, continue to train your model, and create your dashboard and presentation. |  |  |  | Create branches for each member
4 | Put the final touches on your model, database, and dashboard. Lastly, create and deliver your final presentation to your class. |  |  |  | Create branches for each topic

## Sheet2
Project | % | Grade
1st | 19%
2nd | 19%
3rd | 19%
4th | 40%
Assess | 3%
Total | - | 0